## Sheet1
Timeline for 27th Jankidevi Bajaj Puraskar 2019
Sr. No | 27th JBP 2019 Area of activity | Timeline
1 | Posting of the nomination forms | Last week of May 2019
2 | Inviting nomination through member, nonmembers, Ramkrishna Bajaj and Jamnalal Bajaj Awards Mailing list. Announcement through LW fliers, events, website, LW notice board, IMC lift, IMC Weekly Bulletin, regional newspapers across India, Banks, Financial Institutes | June and August 2019
3 | Last date of receiving nominations | 31st August, 2019
4 | Posting of the nominations to the Judges | 1st week of September 2019
5 | First meeting of the Judges (to shortlist the nominations). Introductory and interactive meeting of the Jury members, Awards Committee and Researchers | 3rd week of September 2019
6 | Visit of the researcher to rural areas of the shortlisted nominees | 4th week of September and 1st week of October 2019
7 | Presentation / posting reports of the shortlisted nominations to the panel of Judges | 3rd week of October 2019
8 | Second meeting of the Judges to select the final JBP Awardee | 2nd week of November, 2019
9 | Inform the Awardee & Chief Guest | 2nd week of November, 2019
10 | Announcement of the Awardee to Executive Committee, Sub-Committees, & Press | 2nd week of November, 2019
11 | Announcement through website, IMC weekly bulletin, LW flier, IMC Lift, LW Notice Board | 2nd week of November, 2019
12 | Preparation of press release, copy for booklet, invitation cards, citation, certificate, envelopes, banner, mementoes, related stationery for the function (if necessary), and decision on the arrangement, publicity, menu, invocation singer, presenter etc. | 3th week of November 2019 onwards
13 | Save-the-Date emailers to LW Members and other guests | 1st week December 2019
14 | Invitation to be sent to LW members and Invitees | 2nd week of December 2019
15 | Review the progress of the arrangements, publicity, etc for the Puraskar function | 3rd week of December 2019
16 | Conferment of the Puraskar | 7th January 2020
17 | Thanks letters to Judges, Chief Guest, Winner, and all associated with the arrangements for the Puraskar | Within a week after the function